## Read me
KVD Windpark: flat snagging checklist
RCC framed towers, plaster and paint, aluminium / uPVC windows, wooden internal doors. Phase 1: towers T1, T2, T3, T6, T7 (T4, T5 are Phase 2). 24 floors, 2BHK and 3BHK.
Checklist | Every check item. One row per item, grouped by building element (ceiling, walls, floor, doors, windows, services). ID is what the app stores.
Rooms by flat type | Which rooms each flat type has and which element groups apply to each room. Check counts are live formulas.
Teams | Default responsible team for each item. Edit team names here and in the app's Setup screen.
Severity | What Critical, Major and Minor mean and target fix times.
Handover | Items recorded at handover: gate conditions, meter readings, keys, documents, demonstrations.
Apartment list | Fill this in (yellow cells) and paste into the app's Setup screen to load the actual flats. Row 5 is an example.
Criteria | Tolerances marked 'as per spec' or 'typically' are working defaults. Replace them with the figures in the KVD contract specifications before issue.
Workflow | Open (raised by QC, assigned to team) > Fixed (team marks done with photo) > Closed (QC verifies). QC can reopen. Handover is allowed only when no Critical or Major snag is open.

## Checklist
Checklist master
146 check items. Applies per room as mapped on 'Rooms by flat type'.
ID | Element group | Check | Acceptance criterion / method | Default team | Severity | Applies to rooms
CEIL-01 | Ceiling | Ceiling surface even, no undulation, cracks or patch marks | Torch held flat to the surface; no visible waves or patch outlines | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-02 | Ceiling | No dampness, seepage stains or efflorescence | Look hard below toilets of the flat above and below the terrace on top floors | Waterproofing | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-03 | Ceiling | Paint uniform, no patchiness, brush marks, drips or shade difference | View in daylight and with lights on | Painting | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-04 | Ceiling | Beam soffits and edges straight, arrises true | Sight along the edge; no wavy lines | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-05 | Ceiling | False ceiling / cornice (if any) level, joints invisible, no sagging | Spirit level at 2-3 spots | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-06 | Ceiling | Light and fan points at drawing location, boxes flush, cut-outs neat | Compare with electrical layout | Electrical | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
CEIL-07 | Ceiling | Sprinkler / smoke detector at drawing location, cap removed, not painted over | Compare with fire drawing | Fire Fighting | Critical | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Balcony, Passage / Lobby
WAL-01 | Walls, plaster & paint | Plaster true and plumb | 2 m straight edge in both directions; gap within project spec (typically 3-4 mm) | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-02 | Walls, plaster & paint | No hollow or drummy plaster | Tap with a wooden mallet or knuckle over the full wall | Plaster & POP | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-03 | Walls, plaster & paint | No cracks at RCC-masonry junctions, lintels, frame edges or chase lines | Hairline: mark for mesh repair. Wider than 0.3 mm or recurring: refer to structural | Plaster & POP | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-04 | Walls, plaster & paint | Corners and edges straight, vertical and square; no chipped arrises | Try square at corners; sight along edges | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-05 | Walls, plaster & paint | Paint uniform shade, no patchiness, roller marks, runs, pinholes or putty showing | Daylight and artificial light | Painting | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-06 | Walls, plaster & paint | No paint splashes on switches, frames, glass, tiles or floor | Visual | Painting | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-07 | Walls, plaster & paint | No dampness, blistering, peeling or efflorescence | Check walls shared with toilets, external walls and shafts; moisture meter if available | Waterproofing | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-08 | Walls, plaster & paint | Surface around switchboards, AC sleeves and pipe penetrations neatly finished | Visual | Plaster & POP | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
WAL-09 | Walls, plaster & paint | No nails, binding wire, tie-rod holes or rust marks visible | Visual | Civil & Masonry | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
FLR-01 | Flooring | Tiles / stone of approved make, size and shade; no shade variation in the room | Compare with approved sample; check batch on cartons if still on site | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-02 | Flooring | No hollow-sounding tiles | Tap every tile with a rubber mallet or coin | Tiling & Stone | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-03 | Flooring | Lippage between tiles within limit and floor level | Straight edge across joints; lippage not more than 1 mm; no ponding | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-04 | Flooring | Joints uniform, straight and fully grouted in approved colour | Visual; spacers used; no open joints | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-05 | Flooring | No cracked or broken tiles | Visual | Tiling & Stone | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-06 | Flooring | No chipped edges, scratches or stains on tiles | Visual, torch at low angle | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-07 | Flooring | Cut pieces neat; layout symmetric; no thin slivers at visible edges | Visual | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-08 | Flooring | Door threshold level with floors on both sides, no trip edge | Straight edge across threshold | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
FLR-09 | Flooring | Floor clean of cement slurry, grout haze and paint | Visual | Housekeeping | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Utility, Balcony, Passage / Lobby
SKT-01 | Skirting | Skirting height uniform, top edge straight, projection uniform | Visual, measure at 2-3 points | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
SKT-02 | Skirting | No gap between skirting and floor; joints aligned with floor joints | Visual | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
SKT-03 | Skirting | No loose or hollow skirting pieces | Tap test | Tiling & Stone | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Passage / Lobby
DRI-01 | Internal wooden door | Frame plumb and square, firmly fixed; gap to wall filled and finished | Spirit level on jambs; push test on frame | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-02 | Internal wooden door | Frame free of cracks, splits and termite signs | Visual along full length, specially the bottom | Carpentry (wooden doors) | Major | Bedroom, Toilet
DRI-03 | Internal wooden door | Shutter flat, not warped; veneer / laminate not delaminated, dented or scratched | Straight edge diagonally on shutter face | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-04 | Internal wooden door | Uniform gap between shutter and frame; clearance under shutter as per spec | About 3 mm at sides and top; confirm bottom gap with spec (usually 6-10 mm) | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-05 | Internal wooden door | Shutter swings full without binding and stays where left half-open | Open and close 5 times | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-06 | Internal wooden door | Hinges: minimum 3 nos, all screws fitted, no squeak | Count screws | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-07 | Internal wooden door | Lock / latch works, strike plate aligned, all keys operate | Try every key; latch engages without pushing the door | Carpentry (wooden doors) | Major | Bedroom, Toilet
DRI-08 | Internal wooden door | Handles, tower bolts and door stopper fitted, tight and undamaged | Visual and hand test | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-09 | Internal wooden door | Polish / paint / laminate edges uniform; all six edges of shutter sealed | Check top and bottom edges with a mirror | Carpentry (wooden doors) | Minor | Bedroom, Toilet
DRI-10 | Internal wooden door | Toilet door: water-resistant shutter and bottom edge sealed | Confirm spec (WPC / PVC-faced flush) | Carpentry (wooden doors) | Major | Bedroom, Toilet
DRM-01 | Main entrance door | Door make, rating and finish as approved | Check label / spec sheet | Carpentry (wooden doors) | Major | Foyer / Entrance
DRM-02 | Main entrance door | Main lock and night latch work; all keys operate | Try every key from both sides | Carpentry (wooden doors) | Major | Foyer / Entrance
DRM-03 | Main entrance door | Door viewer fitted at correct height with clear view | About 1500 mm from floor | Carpentry (wooden doors) | Minor | Foyer / Entrance
DRM-04 | Main entrance door | Door closer (if provided) closes and latches smoothly | Release from fully open 3 times | Carpentry (wooden doors) | Minor | Foyer / Entrance
DRM-05 | Main entrance door | Flat number plate fixed with correct number | Visual | Civil & Masonry | Minor | Foyer / Entrance
DRM-06 | Main entrance door | Marble / granite threshold level; no gap under door on lobby side | Visual | Tiling & Stone | Minor | Foyer / Entrance
DRM-07 | Main entrance door | Smoke / weather seal (if specified) continuous | Visual | Carpentry (wooden doors) | Minor | Foyer / Entrance
WIN-01 | Windows & sliding doors (aluminium / uPVC) | Profile, colour and make as approved; frame plumb and square | Spirit level; compare with approved sample | Aluminium / uPVC | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-02 | Windows & sliding doors (aluminium / uPVC) | Frame-to-wall joint sealed inside and outside; no gaps or daylight | Visual from inside with room lights off | Aluminium / uPVC | Major | Living / Dining, Bedroom, Kitchen, Balcony
WIN-03 | Windows & sliding doors (aluminium / uPVC) | No leakage under water test | Hose on the outside for 10-15 min; check frame, sill and glass edges | Aluminium / uPVC | Major | Living / Dining, Bedroom, Kitchen, Balcony
WIN-04 | Windows & sliding doors (aluminium / uPVC) | Sashes slide / open smoothly; rollers free; no rattle | Operate full travel 5 times | Aluminium / uPVC | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-05 | Windows & sliding doors (aluminium / uPVC) | Locks, handles and crescent locks engage fully; friction stays hold | Operate each | Aluminium / uPVC | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-06 | Windows & sliding doors (aluminium / uPVC) | No cracked or broken glass | Visual | Glass & Glazing | Major | Living / Dining, Bedroom, Kitchen, Balcony
WIN-07 | Windows & sliding doors (aluminium / uPVC) | Glass of correct type (toughened / frosted in toilets), no scratches or bubbles, labels removed | Check toughened stamp | Glass & Glazing | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-08 | Windows & sliding doors (aluminium / uPVC) | Gaskets and brush seals complete; glazing beads tight | Run a finger along | Aluminium / uPVC | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-09 | Windows & sliding doors (aluminium / uPVC) | Drainage slots in bottom track open; track clear of mortar | Pour water in the track; it should drain out | Aluminium / uPVC | Major | Living / Dining, Bedroom, Kitchen, Balcony
WIN-10 | Windows & sliding doors (aluminium / uPVC) | Mosquito mesh shutter fitted and slides (if in scope) | Operate | Aluminium / uPVC | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-11 | Windows & sliding doors (aluminium / uPVC) | Sill slopes outward; external sill has drip groove; joints sealed | Visual, spirit level | Tiling & Stone | Minor | Living / Dining, Bedroom, Kitchen, Balcony
WIN-12 | Windows & sliding doors (aluminium / uPVC) | Safety grill / child guard on low-sill windows as specified | Low sill = below about 900 mm | MS / SS Fabrication | Critical | Living / Dining, Bedroom, Kitchen, Balcony
WIN-13 | Windows & sliding doors (aluminium / uPVC) | Protective film removed; no cement or paint on frames | Visual | Housekeeping | Minor | Living / Dining, Bedroom, Kitchen, Balcony
ELC-01 | Electrical points | Switches and sockets as per layout: count, position and height | Compare with electrical layout | Electrical | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
ELC-02 | Electrical points | Plates level and flush, all screws and caps fitted, no cracked plates | Visual | Electrical | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
ELC-03 | Electrical points | Every switch controls its point; every socket passes socket tester | Socket tester for polarity and earth | Electrical | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
ELC-04 | Electrical points | Fan hook in RCC at fan point, secure; regulator point provided | Pull test on hook | Electrical | Major | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
ELC-05 | Electrical points | No loose wires or open boxes; blanking plates on unused boxes | Visual | Electrical | Critical | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
ELC-06 | Electrical points | TV / data / telephone points as per layout with draw wire in conduit | Visual | Electrical | Minor | Foyer / Entrance, Living / Dining, Bedroom, Kitchen, Toilet, Utility, Passage / Lobby
AC-01 | Air-conditioning provision | AC socket (16/20 A) near indoor unit location at correct height | Compare with layout | Electrical | Minor | Living / Dining, Bedroom
AC-02 | Air-conditioning provision | AC sleeve through wall at correct position, sloping out, capped | Visual | HVAC | Minor | Living / Dining, Bedroom
AC-03 | Air-conditioning provision | Condensate drain provision connected and tested | Pour water into drain point; confirm discharge | HVAC | Major | Living / Dining, Bedroom
AC-04 | Air-conditioning provision | Outdoor unit ledge / bracket position safe and reachable for service | Visual from balcony / ledge | HVAC | Minor | Living / Dining, Bedroom
AC-05 | Air-conditioning provision | Pre-installed copper piping (if any) pressure tested and capped | Test record | HVAC | Minor | Living / Dining, Bedroom
BR-01 | Bedroom extras | Wardrobe (if in scope): shutters aligned, hinges, handles and drawers work, no swelling | Operate each shutter and drawer | Carpentry (wooden doors) | Minor | Bedroom
BR-02 | Bedroom extras | Bedside switches / two-way switching as per layout | Test both ends | Electrical | Minor | Bedroom
FOY-01 | Foyer extras | Video door phone / intercom calls security and lobby | Place a test call both ways | Electrical | Major | Foyer / Entrance
FOY-02 | Foyer extras | Bell push outside and chime inside work | Test | Electrical | Minor | Foyer / Entrance
WET-01 | Wet area floor & waterproofing | Waterproofing done and 72-hr ponding test record available | Check QA record for this flat | Waterproofing | Critical | Toilet
WET-02 | Wet area floor & waterproofing | No dampness in ceiling of flat below or adjoining walls | Check the flat below at the same position | Waterproofing | Critical | Toilet
WET-03 | Wet area floor & waterproofing | Floor slopes to floor trap with no ponding | Pour a bucket of water; about 1:100 slope | Tiling & Stone | Major | Toilet
WET-04 | Wet area floor & waterproofing | Floor trap with grating, water seal present, grating flush with tiles | Visual; pour water to check seal | Plumbing & Sanitary | Major | Toilet
WET-05 | Wet area floor & waterproofing | Shower area level drop / step as specified | Visual | Tiling & Stone | Minor | Toilet
WET-06 | Wet area floor & waterproofing | Joints around trap, WC and pipe entries sealed (epoxy / silicone) | Visual | Plumbing & Sanitary | Major | Toilet
DAD-01 | Wall tiles / dado | Dado to specified height; top edge straight and finished | Measure; trim / bullnose as spec | Tiling & Stone | Minor | Toilet, Utility
DAD-02 | Wall tiles / dado | No hollow wall tiles | Tap every tile | Tiling & Stone | Major | Toilet, Utility
DAD-03 | Wall tiles / dado | Joints aligned with floor joints, uniform, grout / epoxy filled | Visual | Tiling & Stone | Minor | Toilet, Utility
DAD-04 | Wall tiles / dado | Cut-outs around pipes, CP fittings and switches neat, no cracks | Visual | Tiling & Stone | Minor | Toilet, Utility
DAD-05 | Wall tiles / dado | No cracked or chipped tiles; lippage within 1 mm | Straight edge | Tiling & Stone | Minor | Toilet, Utility
DAD-06 | Wall tiles / dado | External corners with trims or mitred edges, straight | Visual | Tiling & Stone | Minor | Toilet, Utility
SAN-01 | Sanitary ware | WC of approved make, firmly fixed, level, no rocking; seat cover fitted | Push test; spirit level | Plumbing & Sanitary | Major | Toilet
SAN-02 | Sanitary ware | Flush works, cistern refills and stops; both dual-flush buttons work | Flush 3 times | Plumbing & Sanitary | Major | Toilet
SAN-03 | Sanitary ware | WC joint to floor / wall sealed; no leak on flush | Tissue test at base after flushing | Plumbing & Sanitary | Major | Toilet
SAN-04 | Sanitary ware | Wash basin level and firmly fixed; counter / pedestal stable | Push test | Plumbing & Sanitary | Minor | Toilet
SAN-05 | Sanitary ware | Basin waste, bottle trap and overflow work; no leak underneath | Fill basin and release | Plumbing & Sanitary | Major | Toilet
SAN-06 | Sanitary ware | No chips, cracks or crazing on ceramic ware | Visual, torch | Plumbing & Sanitary | Major | Toilet
SAN-07 | Sanitary ware | Health faucet, towel rail, robe hook, soap dish, paper holder, mirror fitted as spec | Check against accessories list | Plumbing & Sanitary | Minor | Toilet
SAN-08 | Sanitary ware | Silicone around basin and counter neat and continuous | Visual | Plumbing & Sanitary | Minor | Toilet
CPF-01 | CP fittings & water supply | Hot and cold water at every outlet; hot on left | Run every outlet | Plumbing & Sanitary | Major | Toilet
CPF-02 | CP fittings & water supply | Diverter, shower and spout operate; no drip after closing | Operate each | Plumbing & Sanitary | Minor | Toilet
CPF-03 | CP fittings & water supply | Flow and pressure adequate | Check at the highest outlet; compare top floors | Plumbing & Sanitary | Major | Toilet
CPF-04 | CP fittings & water supply | Concealed stop-cocks accessible, working and identified | Operate each | Plumbing & Sanitary | Minor | Toilet
CPF-05 | CP fittings & water supply | Geyser point (socket + inlet / outlet) at correct height; geyser (if supplied) tested | Visual; run hot water | Plumbing & Sanitary | Major | Toilet
CPF-06 | CP fittings & water supply | Wall flanges flush on all concealed outlets | Visual | Plumbing & Sanitary | Minor | Toilet
CPF-07 | CP fittings & water supply | No leak at any joint after running all outlets for 5 min | Check below basin, behind WC, in shaft | Plumbing & Sanitary | Major | Toilet
CPF-08 | CP fittings & water supply | Chrome finish free of scratches, rust or pitting | Visual | Plumbing & Sanitary | Minor | Toilet
EXH-01 | Ventilation | Exhaust fan point / fan works; cowl or louvre fitted outside | Switch on | Electrical | Minor | Toilet
EXH-02 | Ventilation | Ventilator frame, louvres and glass intact and operable | Operate | Aluminium / uPVC | Minor | Toilet
EXH-03 | Ventilation | False ceiling access panel (if any) for plumbing / geyser | Open panel | Plaster & POP | Minor | Toilet
KIT-01 | Kitchen | Platform level, firmly supported, height as spec, front edge moulded and polished | Spirit level; typically 820-850 mm | Tiling & Stone | Minor | Kitchen
KIT-02 | Kitchen | Platform joints epoxy filled; no cracks in stone; backsplash joint sealed | Visual | Tiling & Stone | Minor | Kitchen
KIT-03 | Kitchen | Sink fitted level and sealed; drains fast; no leak below | Fill and release sink | Plumbing & Sanitary | Major | Kitchen
KIT-04 | Kitchen | Sink tap / mixer works, aerator fitted | Operate | Plumbing & Sanitary | Minor | Kitchen
KIT-05 | Kitchen | Dado above platform to spec height; joints aligned | Measure | Tiling & Stone | Minor | Kitchen
KIT-06 | Kitchen | Appliance points (chimney, microwave, fridge, RO, dishwasher) at correct location and rating | Compare with layout | Electrical | Minor | Kitchen
KIT-07 | Kitchen | Chimney / exhaust core cut with cowl to outside | Visual | HVAC | Minor | Kitchen
KIT-08 | Kitchen | PNG gas pipe, isolation valve and meter point; leak test certificate | Certificate from gas agency | Plumbing & Sanitary | Critical | Kitchen
KIT-09 | Kitchen | RO / purifier inlet and drain point provided | Visual | Plumbing & Sanitary | Minor | Kitchen
KIT-10 | Kitchen | Modular kitchen (if in scope): shutters aligned, hinges and channels work, no swelling | Operate each | Carpentry (wooden doors) | Minor | Kitchen
UTL-01 | Utility | Washing machine inlet tap and drain point; socket at safe height | Visual; socket clear of splash zone | Plumbing & Sanitary | Minor | Utility
UTL-02 | Utility | Floor slopes to drain; no ponding | Bucket test | Tiling & Stone | Major | Utility
UTL-03 | Utility | Utility sink / tap works (if in scope) | Operate | Plumbing & Sanitary | Minor | Utility
UTL-04 | Utility | No dampness on walls or ceiling below | Check flat below | Waterproofing | Major | Utility
BAL-01 | Balcony | Railing height as per spec / bye-laws from finished floor; rigid, no shake | Measure; push hard at mid-span | MS / SS Fabrication | Critical | Balcony
BAL-02 | Balcony | Baluster gap within 100 mm; no climbable horizontal members | Measure | MS / SS Fabrication | Critical | Balcony
BAL-03 | Balcony | Glass railing (if any): toughened laminated glass, clamps tight, edges polished | Check stamp and fixings | Glass & Glazing | Critical | Balcony
BAL-04 | Balcony | Railing welds ground, finish free of rust; anchors grouted and sealed | Visual | MS / SS Fabrication | Minor | Balcony
BAL-05 | Balcony | Floor slopes away from the flat to outlet; no ponding | Bucket test | Tiling & Stone | Major | Balcony
BAL-06 | Balcony | Rainwater outlet with grating, connected and flowing | Pour water | Plumbing & Sanitary | Major | Balcony
BAL-07 | Balcony | Level drop / upstand at balcony door stops water entering the flat | Visual; water test | Civil & Masonry | Major | Balcony
BAL-08 | Balcony | External paint on parapet and walls uniform; no cracks or seepage | Visual | Painting | Minor | Balcony
BAL-09 | Balcony | Drip groove under slab edge continuous | Visual | Plaster & POP | Minor | Balcony
BAL-10 | Balcony | Light point and weatherproof socket as per layout | Test | Electrical | Minor | Balcony
UNT-01 | Whole flat / services | Room dimensions spot-checked against sale drawing | Laser measure main rooms | Civil & Masonry | Major | Whole flat
UNT-02 | Whole flat / services | Floor-to-ceiling height as per drawing | Laser measure | Civil & Masonry | Minor | Whole flat
UNT-03 | Whole flat / services | No cracks in beams, columns or slabs; no exposed steel or honeycombing | Report any to structural consultant | Civil & Masonry | Critical | Whole flat
UNT-04 | Whole flat / services | DB: MCB ratings as per schedule; RCCB trips on test button and socket tester | Press RCCB test; 30 mA tester | Electrical | Critical | Whole flat
UNT-05 | Whole flat / services | DB circuits labelled; cover and blanks fitted; no exposed live parts | Visual | Electrical | Major | Whole flat
UNT-06 | Whole flat / services | Insulation resistance and earth continuity test record for this flat | IR test record per spec (typically 1 MΩ or more) | Electrical | Major | Whole flat
UNT-07 | Whole flat / services | Electricity meter installed, sealed, mapped to this flat; reading noted | Switch off flat main and confirm meter stops | Electrical | Major | Whole flat
UNT-08 | Whole flat / services | DG backup circuits work on changeover | Coordinate DG test | Electrical | Major | Whole flat
UNT-09 | Whole flat / services | Internal water line hydro-test record; no pressure drop | Test record | Plumbing & Sanitary | Major | Whole flat
UNT-10 | Whole flat / services | Water meter (if any) installed and mapped; reading noted | Visual | Plumbing & Sanitary | Minor | Whole flat
UNT-11 | Whole flat / services | No sewer smell; all traps charged with water | Walk through with doors closed | Plumbing & Sanitary | Major | Whole flat
UNT-12 | Whole flat / services | Plumbing shaft access door fitted; no leak in shaft | Open and inspect | Plumbing & Sanitary | Major | Whole flat
UNT-13 | Whole flat / services | Sprinklers / smoke detectors as per fire drawing; caps removed | Compare with fire NOC drawings | Fire Fighting | Critical | Whole flat
UNT-14 | Whole flat / services | Intercom handset works; extension number noted | Test call | Electrical | Minor | Whole flat
UNT-15 | Whole flat / services | Fittings of approved make (random check of tiles, CP, sanitary, switches, locks) | Compare with spec sheet | Civil & Masonry | Minor | Whole flat
UNT-16 | Whole flat / services | Anti-termite / pest control record available | Record | Civil & Masonry | Minor | Whole flat
UNT-17 | Whole flat / services | Deep cleaning done; debris, packaging and stickers removed | Visual | Housekeeping | Minor | Whole flat
UNT-18 | Whole flat / services | Lobby in front of flat: finishes, lighting and fire door OK | Log common-area issues separately | Civil & Masonry | Minor | Whole flat

## Rooms by flat type
Rooms by flat type
Check count = number of checklist rows whose element group is listed for the room (live formula).
Flat type | Room key | Room | Room kind | Element groups | Checks
2BHK | foyer | Foyer | Foyer / Entrance | CEIL, WALL, FLR, SKT, DRM, ELC, FOY | 43
2BHK | living | Living / Dining | Living / Dining | CEIL, WALL, FLR, SKT, WIN, ELC, AC | 52
2BHK | kitchen | Kitchen | Kitchen | CEIL, WALL, FLR, SKT, WIN, ELC, KIT | 57
2BHK | utility | Utility | Utility | CEIL, FLR, DAD, UTL, ELC | 32
2BHK | passage | Passage | Passage / Lobby | CEIL, WALL, FLR, SKT, ELC | 34
2BHK | bed1 | Master Bedroom | Bedroom | CEIL, WALL, FLR, SKT, DRI, WIN, ELC, AC, BR | 64
2BHK | bed2 | Bedroom 2 | Bedroom | CEIL, WALL, FLR, SKT, DRI, WIN, ELC, AC, BR | 64
2BHK | toi1 | Master Toilet | Toilet | CEIL, DRI, WET, DAD, SAN, CPF, EXH, ELC | 54
2BHK | toi2 | Common Toilet | Toilet | CEIL, DRI, WET, DAD, SAN, CPF, EXH, ELC | 54
2BHK | bal1 | Living Balcony | Balcony | CEIL, FLR, WIN, BAL | 39
2BHK | bal2 | Bedroom Balcony | Balcony | CEIL, FLR, WIN, BAL | 39
2BHK | flat | Whole flat & services | Whole flat | UNT | 18
|  |  |  | Total checks per 2BHK flat | 550
3BHK | foyer | Foyer | Foyer / Entrance | CEIL, WALL, FLR, SKT, DRM, ELC, FOY | 43
3BHK | living | Living / Dining | Living / Dining | CEIL, WALL, FLR, SKT, WIN, ELC, AC | 52
3BHK | kitchen | Kitchen | Kitchen | CEIL, WALL, FLR, SKT, WIN, ELC, KIT | 57
3BHK | utility | Utility | Utility | CEIL, FLR, DAD, UTL, ELC | 32
3BHK | passage | Passage | Passage / Lobby | CEIL, WALL, FLR, SKT, ELC | 34
3BHK | bed1 | Master Bedroom | Bedroom | CEIL, WALL, FLR, SKT, DRI, WIN, ELC, AC, BR | 64
3BHK | bed2 | Bedroom 2 | Bedroom | CEIL, WALL, FLR, SKT, DRI, WIN, ELC, AC, BR | 64
3BHK | bed3 | Bedroom 3 | Bedroom | CEIL, WALL, FLR, SKT, DRI, WIN, ELC, AC, BR | 64
3BHK | toi1 | Master Toilet | Toilet | CEIL, DRI, WET, DAD, SAN, CPF, EXH, ELC | 54
3BHK | toi2 | Toilet 2 | Toilet | CEIL, DRI, WET, DAD, SAN, CPF, EXH, ELC | 54
3BHK | toi3 | Toilet 3 | Toilet | CEIL, DRI, WET, DAD, SAN, CPF, EXH, ELC | 54
3BHK | bal1 | Living Balcony | Balcony | CEIL, FLR, WIN, BAL | 39
3BHK | bal2 | Bedroom Balcony | Balcony | CEIL, FLR, WIN, BAL | 39
3BHK | flat | Whole flat & services | Whole flat | UNT | 18
|  |  |  | Total checks per 3BHK flat | 668

## Teams
Teams
Default owner for snags raised against each item. Counts are live formulas.
Team ID | Team | Checklist items owned | of which Critical
civil | Civil & Masonry | 9 | 1
plaster | Plaster & POP | 10 | 0
paint | Painting | 4 | 0
tiling | Tiling & Stone | 26 | 0
carpentry | Carpentry (wooden doors) | 17 | 0
fenestration | Aluminium / uPVC | 9 | 0
glazing | Glass & Glazing | 3 | 1
electrical | Electrical | 20 | 2
plumbing | Plumbing & Sanitary | 29 | 1
waterproofing | Waterproofing | 5 | 2
hvac | HVAC | 5 | 0
fire | Fire Fighting | 2 | 2
fabrication | MS / SS Fabrication | 4 | 3
housekeeping | Housekeeping | 3 | 0

## Severity
Severity
Used on every snag.
Severity | Meaning | Items in checklist
Critical | Safety, structure, water ingress or statutory item. Blocks handover. Target fix: 48 hours. | 12
Major | Function affected or visible defect a buyer will reject. Blocks handover. Target fix: 7 days. | 46
Minor | Cosmetic or finishing. Can be accepted by the buyer at handover with a fix date. Target fix: 14 days. | 88

## Handover
Handover record
Captured in the app's Handover tab for each flat, with customer and company signatures.
Section | Item | Record
Before handover | No Critical or Major snag open (checked automatically) | System
Before handover | Inspection 100% complete (checked automatically) | System
Before handover | Occupancy certificate received / possession offered | Tick
Before handover | CRM confirms dues cleared | Tick
Meter readings | Electricity meter (kWh) | Reading
Meter readings | DG / prepaid meter | Reading
Meter readings | Water meter | Reading
Meter readings | PNG gas meter | Reading
Keys handed (count) | Main door | Number
Keys handed (count) | Bedroom doors | Number
Keys handed (count) | Toilet doors | Number
Keys handed (count) | Balcony / window locks | Number
Keys handed (count) | Letter box | Number
Keys handed (count) | DB / meter box | Number
Keys handed (count) | Access cards / RFID tags | Number
Documents handed | Possession letter | Tick
Documents handed | Joint inspection report (snag list) signed | Tick
Documents handed | Warranty cards: CP and sanitary fittings | Tick
Documents handed | Warranty: windows and main door lock | Tick
Documents handed | Warranty: modular kitchen / appliances (if any) | Tick
Documents handed | As-built electrical and plumbing layouts | Tick
Documents handed | Owner's manual (incl. no drilling / core cutting in RCC, waterproofing care) | Tick
Documents handed | Maintenance agreement and RWA forms | Tick
Documents handed | Parking allotment letter | Tick
Shown to customer | DB, MCB and RCCB reset shown | Tick
Shown to customer | Water isolation valves shown | Tick
Shown to customer | Gas isolation valve shown | Tick
Shown to customer | Intercom and video door phone shown | Tick
Shown to customer | Smoke detector, sprinkler and escape route explained | Tick
Shown to customer | Window locks and mesh shown | Tick
Acceptance | Customer name | Entry
Acceptance | Customer phone | Entry
Acceptance | Customer remarks | Entry
Acceptance | Minor snags accepted with fix date | Entry
Acceptance | Customer signature | Entry
Acceptance | Company representative signature | Entry
Acceptance | Handover date | Entry

## Apartment list
Apartment list
Fill yellow cells from row 6 down. Copy columns A-E (with header row) and paste into the app: Setup > Apartment list.
Tower | Floor | Flat no. | Type | Carpet area (sq ft)
T1 | 12 | 1203 | 3BHK | 1450 | Example row: delete before pasting